## Overall Breakdown
Legend
| CMPUT301F15T05 | Planned Work
| Release Planning | Actual Work
|  | October | [7 empty] | Project Part 2 | [16 empty] | Project Part 3 | [5 empty] | November |  |  |  |  | Project Part 4 | [23 empty] | Project Part 5 |  | Demo
|  | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F
# | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
2 | Project Part 2
2.1 | Requirements Specification | bar: October T 6 to Project Part 2 F 9
2.2 | UI Mockup and Storyboard | bar: October T 6 to Project Part 2 F 9
2.3 | Release Planning | bar: October T 6 to Project Part 2 F 9
2.4 | Glossary and Information Souces | bar: October T 6 to Project Part 2 F 9
3 | Project Part 3
3.1 | Addressing Feedback
3.1a | In Lab Feedback | bar: Project Part 2 W 14
3.1b | Remediation | bar: Project Part 2 W 14 to Project Part 2 S 18
3.2 | Object-Orientated Analysis and Design
3.2a | UML First Draft | bar: Project Part 2 M 12 to Project Part 2 F 16
3.2b | UML Group Review | bar: Project Part 2 F 16 to Project Part 2 S 18
3.2c | UML Final Copy | bar: Project Part 2 S 18 to Project Part 2 R 22
4 | Project Part 4
4.1 | Addressing Feedback
4.1a | In Lab Feedback | bar: Project Part 3 W 28
4.1b | Remediation | bar: Project Part 3 W 28 to November S 1
4.2 | Code Base of Prototype
4.2a | Skeleton Code Based on UML | bar: Project Part 2 S 17 to Project Part 2 T 20
4.2b | 50% Feature Functionality | bar: Project Part 2 T 20 to Project Part 3 R 29
4.2c | Group Code Review | bar: Project Part 3 R 29 to November S 1
4.3 | Code Documentation
4.3a | Introductory Comments | bar: Project Part 2 S 17 to Project Part 2 R 22
4.3b | Javadoc's | bar: Project Part 3 R 29 to November S 1
4.4 | Test Cases
4.4a | Skeleton Tests | bar: Project Part 2 S 17 to Project Part 2 R 22
4.4b | Complete Tests and Run | bar: Project Part 3 R 29 to November S 1
4.5 | Object-Orientated Design
4.5a | Update UML Diagrams | bar: Project Part 3 R 29 to November S 1
4.6 | Release Planning
4.6a | Evaluate Part 4 Progress | bar: Project Part 2 W 21 to Project Part 2 R 22
4.6b | Re-evaluate Part 5 Goals | bar: Project Part 2 W 21 to Project Part 2 R 22; Project Part 3 R 29 to November S 1
4.7 | Reuse Statement
4.7a | Credit Reused Code | bar: Project Part 3 R 29 to November S 1
5 | Project Part 5
5.1 | Addressing Feedback
5.1a | In Lab Feedback | bar: Project Part 4 W 11
5.1b | Remediation | bar: Project Part 4 W 11 to Project Part 4 S 15
5.2 | Code Base of Prototype
5.2a | Remaining Feature Functionality | bar: November T 3 to Project Part 4 W 18
5.2b | User Interface Finalization | bar: Project Part 4 S 15 to Project Part 4 S 22
5.2c | Group Code Review | bar: Project Part 4 S 21 to Project Part 4 T 24
5.3 | Code Documentation
5.3a | Complete Javadoc's | bar: Project Part 4 W 25 to Project Part 4 F 27
5.3b | Note Outstanding Issues | bar: Project Part 4 S 28 to Project Part 4 S 29
5.4 | Test Cases
5.4a | Complete JUnit Tests (for every use case) | bar: Project Part 4 W 25 to Project Part 4 S 29
5.5 | Requirements Specification
5.5a | Update Use Cases and User Stories | bar: Project Part 4 W 25 to Project Part 4 S 29
5.6 | Object-Orientated Design
5.6a | Confirm Code Parallels UML | bar: Project Part 4 S 21 to Project Part 4 T 24
5.6b | Update UML | bar: Project Part 4 W 25 to Project Part 4 S 29
5.7 | Planning
5.7a | Evaluate Part 5 Progress | bar: Project Part 4 W 25 to Project Part 4 S 29
5.7b | Plan for Next Iteration | bar: Project Part 4 W 25 to Project Part 4 S 29
5.8 | Reuse Statement
5.8a | Credit Reused Code
5.9 | Demo Presentation
5.9a | Prepare Video | bar: Project Part 4 S 28 to Project Part 4 S 29
5.9b | Practice Runs | bar: Project Part 4 S 29 to Project Part 5 T 1
5.1 | Bonus: Video Demo
5.10a | See 5.9a | bar: Project Part 4 S 28 to Project Part 4 S 29

## Project Breakdown
CMPUT301F15T05
Release Planning
Project Part | Use Case | Related User Stories | Dependent Use Cases
Project Part 4
| 1: Add Item | US01.01.01, US01.06.01 | 2
| 2: Browse Inventory | US01.02.01
| 3: View Item | US01.03.01 | 2
| 4: Set Public | US01.03.01
| 5: Modify Items | US01.04.01
| 6: Delete Item | US01.05.01
| 7: Minimum Navigation | US01.07.01 | 5
| 8: Find User | US02.01.01
| 9: Add Friend | US02.02.01 | 8
| 10: Remove Friend | US02.03.01
| 11: User Profile | US02.04.01
| 12: View Profiles | US02.05.01 | 8, 11
| 13: Search Friends Inventory | US03.01.01, US03.01.02, US03.01.03
| 14: Make Items Visible | US03.02.01
| 16: Notify | US04.02.01 | 15
| 25: Add Photo | US06.01.01
| 26: View Photo | US06.02.01
| 27: Delete Photo | US06.03.01
| 34: Edit Profile | US10.02.01 | 11
Project Part 5
| 23: Complete Trade | US04.10.01
| 24: Trade Status | US04.11.01, US04.12.01
| 15: Trade with Friend | US04.01.01 | 16
| 17:Respond to Trade | US04.03.01 | 15
| 18: Counter a Trade | US04.04.01 | 15, 17
| 19: Edit Trade | US04.05.01 | 15
| 20: Delete Trade | US04.06.01 | 15
| 21: Email Parties | US04.07.01 | 15, 17
| 22: See Trades | US04.08.01, US04.09.01
| 28: Restrict Image Size | US06.04.01
| 29: Download Photo | US06.05.01 | 24
| 30: Add Item Offline | US09.01.01 | 1
| 31: Make Trades Offline | US09.02.01
| 32: Browse Friends Offline | US09.03.01
| 33: Download Image Preference | US10.01.01
| 35: Default Geolocation | US11.01.01 | 1
| 36: Search Location | US11.02.01
| 37: Get Geolocation | US11.03.01
| 38: Different Geolocation | US11.04.01 | 5, 35
Future Release
| Top Traders | US12.01.01
| Item Cloning | US13.01.01 | 1